## Description
Text Transformer
For people working with text data, our Text Transformer application will allow you to transform text data (e.g. change case, eliminate duplicates, etc.). The application will be available via GUI as well as remote API, thanks to which it will be possible to integrate it with existing tools.

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps | 15 | 1h | 1 | o Input in the form of text and transformation sequence (names) o Input and output in JSON format o REST API allows to run any currently implemented transformation or transformation sequence
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) | 12 | 1h | 0.5 | o Change case of letters - set of three transformations (upper, lower, capitalize) • upper - all letters to uppercase: upper -> UPPER • lower – all letters to lowercase: Lower -> lower • capitalize – the first letter in each word to uppercase: capitalize text -> Capitalize Text • Support for letters from the English alphabet (UTF-8)
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse) | 10 | 1h | 0.5 | • Preserving the positions of upper and lower case letters: MirEk -> KerIm • Reverse sequence of characters • Support for all UTF-8 characters
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated | 10 | 2h | 1 | • conversion of integers to 1000 • conversion of floating point numbers to hundredths
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate | 10 | 2h | 0.5 | • Acronym expansion: for example -> e.g. • Acronym expansion: among others -> i.a. • Acronym expansion: and so on -> aso • Works regardless of case
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) | 10 | 1h | 0.5 | • prof. -> professor • dr -> doctor • e.g. -> for example • aso -> and so on • Preserves case: E.g. -> For example
As a user I can convert text to Latex supported format (special characters) -> (John Smith & Sons -> John Smith \& Sons) | 2 | 1h | 0.5 | • & -> \& • $ -> \$
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) | 1 | 3h | 1 | • Convert two repeated words to one: to to -> to • Convert any number of words repeated: to to to -> to • Replace all repetitions within a text: to to after after -> to after • Works well with all UTF-8 characters
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal: Deliver working Text Transformer API with 9 Transformer Services
Product Backlog Item | Tasks | Labour intensity
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps |  | 1h
| Setup DTOs for data transfer from and to the controller | 15min
| Setup TransformationServiceRegistry | 15min
| Call an aproperiate Transformer in the list provided in the request body | 15min
| Prepare TransformerService (Abstract Class for the Decorator Pattern) | 15min
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) |  | 1h
| Create ToUpperTransformerService | 15min
| Create ToLowerTransformerService | 15min
| Create CapitalizeTransformerService | 15min
| Integrate with existing Transformers | 15min
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse) |  | 1h
| Create ReverseTransformerService | 30min
| Integrate with existing Transformers | 30min
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated |  | 2h
| Setup supported numbers swap list | 15min
| Create Nums2TextTransformerService | 1.5h
| Integrate with existing Transformers | 15min
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate |  | 2h
| Setup supported acronyms | 15min
| Create Word2AcronymTransformerService | 1.5h
| Integrate with existing Transformers | 15min
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) |  | 1h
| Setup supported acronyms | 15min
| Create Acronym2WordTransformerService | 30min
| Integrate with existing Transformers | 15min
As a user I can convert text to Latex supported format (special characters) -> (John Smith & Sons -> John Smith \& Sons) |  | 1h
| Create LatexTransformerService | 45min
| Integrate with existing Transformers | 15min
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) |  | 3h
| Write the algorithm for removing repeated words | 2.5h
| Integrate with existing Transformers | 30min
[Other]
| Setup logger | 15min
| Setup CI/CD to build docs | 30min
| Setup CI/CD to build JAR | 30min
| Draw UML | 20min

## Sprint #2 Backlog
Sprint Goal: Deliver working UI for Text Transformers and increase test coverage
Product Backlog Item | Tasks | Labour intensity
As a user, I can utilise the application via the user interface |  | 4h
| Create working UI for text transformers | 4h
[Other] |  | 3h
| Create 20 unit tests methods for classes | 1.5h
| Create 15 mock objects in those unit tests | 1.5h
| Write javadoc for 7 classes | 1h